Minutes of review meeting held on 24.3.15 with Health & disability ADMCs working at dist. level in the conference hall of MEPMA.

Participants:

- AMD, (Admin) from MEPMA,

- SMC- SS, BT & HND, and Jr. SMC from MEPMA.

- IT person from MEPMA

- ADMCs of E.G,Chittoor, Prakasam, Kadapa, Nellore, Kurnool, Krishna, Visakhapatnam, and Gunturdists.

The following suggestions/ recommendations were made by the participants.

- Reviewed Municipality wise updation of members of MAS and instructed to complete the updation on or before 28.3.15 (municipality wise status enclosed).

- Till date only Prakasam & East Godavari districts started the trainings for MAS members. Project Directors are requested to start the trainings immediately under intimation to the DM&HO s.

- Weekly progress on trainings of MAS members is to be sent to MEPMA.

- By 5th of every month ULB wise status report on health savings is to be sent to MEPMA and ensure that health savings are to be initiated in all SLFs .

- Ensure that Jeevandhara Generic Medical stores are to be established in all the districts @ 5 per dist. and one in Visakhapatnam by the end of July. (Recorded in Hon’ble Minister’s (MA& UD) review meeting held on 16.2.15 and in 1st EC meeting held on 3.1.15.) Identification of place and beneficiaries are to be done by ADMC- Health and Grounding of units is to be done by the DMC-LH.

- Identification of eligible candidates (B-pharmacy) & selection of 4-5 SHG members for Jeevandhara Generic Medical stores by passing SLF resolution and exposure visit to Kurnool municipality along with DMC-LH & ADMC-H&D is to be completed by 10.4.15.The Project Director, Kurnool has to take necessary action.

- Majority of the districts  have not reached the targets in Formation of SHGs of PWDs in NULM towns for the year 2014-15 .( status report enclosed)

- It is noticed that till date RF to SHGs of PWDs and RO funds have not yet been released by the Project Directors. It is requested to release the funds on or before 31.3.15.( related circulars already  issued)

- Fixed dates are to be followed for monthly meetings of MAS at SLF level.

- Agenda for MAS monthly meetings is to be prepared by the ADMC-Health by attending at least 5-10 MAS meetings.

- By April 10th all the health & disability camps are to be updated in online.

- ADMCs have suggested to take up   issues of PWDs in the first hour of regular meetings at SLF/ TLF level.

- Common group mail IDs is to be created at MEPMA level by IT and communicated to ADMC - Health and existing reports in MEPMA website relating to Health & disability are to be brought under Health & disability Title by IT, MEPMA.